Milestones, Demonstrator Construction 10/06 – 7/07

Tobias Haas

Draft 0

| # | Name | Date | Partner | Description/Remarks |
| --- | --- | --- | --- | --- |
| 1 | TLU | 18 Oct 06 | Bristol | TLU working. Ship to Geneva. |
| 2 | DAQ0 | 18 Oct 06 | Geneva | Bonn+Strasbourg DAQ + TLU work together. |
| 3 | FE0 | 15 Jan 06 | DESY | 15 Populated FE board sets with sensors (limited tests) available. Ship to Ferrara, Geneva, Strasbourg. |
| 4 | EUDRB0 | 15 Jan 06 | Ferrara | EUDRB board partial functionality. Ship to Geneva |
| 5 | DAQ1 | 5 Mar 06 | Geneva | DAQ partially integrated with EUDRB |
| 6 | EUDRB1 | 5 Mar 06 | Ferrara | EUDRB board tested with FE board set and sensor (no sparsification). Ship 1 full set to Geneva. |
| 7 | FE1 | 5 Mar 06 | Strasbourg/Geneva /Ferrara /DESY | FE board sets fully qualified |
| 8 | EUDRB2 | 2 Apr 06 | Ferrara | 2 EUDRB boards synchronized. Ship 1 set to Geneva. |
| 9 | DAQ2 | 30 Apr 06 | Geneva | DAQ fully integrated with two full FE board sets + EUDRB |
| 10 | TB0 | 30 Apr 06 | DESY | Mechanics and TB infrastructure ready for integration |
| 11 | DEMO0 | 2 Jul 06 | DESY | Demonstrator available |